## Pick-list (hidden)
Organisation | Région | CARE | CRS | WaterAid | District | ATS | ALMA | VKN | AMM | HTM | V7V | Commune | Site | Stratégie | Financement | Système | Maître d'œuvre | Entreprise | APS vf le | APD vf le | ESF validé le | Analyse et Dépouillement | AOR | Contrat signé | OS | Démarrage travaux le | Avancement travaux | RT | RP | RD | CDD signé CR le | CDD signé Ese le | Envoi CDD au MEAH le | CDD signé MEAH le | Observations
CARE |  | AMM | ATS | ALMA |  | Toamasina II | Moramanga | Antanifotsy | Manandriana | Vohibato | Vohipeno |  |  | PPP |  | AEPG (BS, BP, PEC) | Sandandrano |  | Date | Date | Date | Date | En cours | Date | Date | Date | Pourcentage | Date | Date | Date | Date | Date | Date | Date
CRS |  | HTM | VKN |  |  | Mahanoro | Ambatondrazaka | Antsirabe II | Fandriana | Lalangina | Ikongo |  |  | PPP+ |  | AEPP (BS, BP, PEC) | Bushproof |  | En cours | En cours | En cours | En cours | Clôturé | - | - | - | - | - | - | - | - | - | - | -
WaterAid |  | V7V |  |  |  | Vatomandry | Amparafaravola | Betafo | Ambositra | Ambalavao | Manakara Atsimo |  |  | Foire (GC to GP) |  | FPMH (PEC) | Zara-Rano |  | #N/A | #N/A | #N/A | #N/A | #N/A
[6 empty] | Brickaville |  |  |  |  | Mananjary |  |  | Manifestation spontanée |  | PPMH (PEC) | DREAH
[11 empty] | Ifanadiana |  |  | Mobilisation VSLA |  | Kiosque (PEC) | AUTRE
[14 empty] | Dotation de matériel |  | Biosand Filter
Autre financement

## Suivi Travaux & CDD (hidden)
Organisation | Région | District | Commune | Site | Stratégie | Financement | Système | Maître d'œuvre | Entreprise | APS vf le | APD vf le | ESF validé le | Analyse et Dépouillement | AOR | Contrat signé le | OS | Démarrage travaux le | Avancement travaux | RT | RP | RD | Retard | CDD signé CR le | CDD signé Ese le | Envoi CDD au MEAH le | CDD signé MEAH le | Superficie BV1 (Ha) | Superficie BV2 (Ha) | Superficie BV3 (Ha) | Superficie captage 9m2) | Volume retenue (m3) | Superficie zone de filtration filtre (m2) | Longueur tuyau amene (km) | Superficie zone de stockage (m2) | Volume stockage (m3) | Longueur conduite de distribution (km) | Superficie monobloc (m2) | Nbre habitants APD 2028-22 | Demande en eau (m3/j) | Situation | Observations
CARE | AMM | Ambositra | Ambalamanakana | Ambalamanakana | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2020-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Ambositra | Ambatofitorahana | Ambatofitorahana | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | Sandandrano | En attente de la remise de l'offre | 2020-06-01 | 2020-09-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | AMM | Ambositra | Ambositra II | Ambositra II | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | DREAH | En attente de la remise de l'offre |  | En cours |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | AMM | Ambositra | Ankazoambo | Ankazoambo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2020-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Ambositra | Ilaka Centre | Ilaka Centre | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | AΠR | 2020-06-01 | 2020-09-30 | 2021-07-22 | 2021-07-01 | Clôturé | 2022-03-18 | 2022-03-30 | 2022-03-31 | 100% | 2022-08-25 | - | - |  | - | - | - | - | [13 empty] | RP et RD | -
CARE | AMM | Ambositra | Ivato | Ivato Centre | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | AΠR | 2020-06-01 | 2020-09-30 | 2021-11-16 | 2021-07-12 | Clôturé | 2021-09-13 | 2021-09-22 | 2021-09-22 | 100% | 2021-12-17 | 2022-01-31 | 2022-08-09 |  | 2022-01-28 | 2022-01-28 | - | - | [13 empty] | Exploitation | -
CARE | AMM | Ambositra | Kianjandrakefina | Kianjandrakefina | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2020-06-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Ambositra | Marosoa | Marosoa | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2020-06-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Ambositra | Sahatsiho Ambohimanjaka | Ambohimanjaka | Autre financement | Privé | FPMH (PEC) | Sandandrano |  | 2020-06-01 | 2020-11-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Ambositra | Tsarasaotra | Tsarasaotra | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | Sandandrano | En attente de la remise de l'offre | 2020-08-01 | 2020-11-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | AMM | Fandriana | Ambohimahazo | Ambohimahazo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2020-06-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Fandriana | Ankarinoro | Ankarinoro | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2020-08-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Fandriana | Fiadanana | Fiadanana | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | Sandandrano | En attente de la remise de l'offre | 2020-09-01 | En cours |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | AMM | Fandriana | Sahamadio Fisakana | Sahamadio | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | DREAH | En attente de la remise de l'offre |  | En cours |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | AMM | Fandriana | Sandrandahy | Sandrandahy | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | Sandandrano | En attente de la remise de l'offre | 2020-09-01 | En cours |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | AMM | Manandriana | Ambatomarina | Ambatomarina | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | ACOGEMA | 2020-07-01 | 2020-09-30 | 2021-06-29 | 2021-08-01 | Clôturé | 2021-10-12 | 2021-10-22 | 2021-10-22 | 100% | 2022-02-04 | 2022-02-19 | - |  | 2022-02-18 | 2022-02-18 | - | - | 25 | [5 empty] | 2.36 |  | 65 | 4.825 | 25 | 3700 | 205 | Attente RD | -
CARE | AMM | Manandriana | Ambohimilanja | Ambohimilanja | Autre financement | Privé | FPMH (PEC) | Sandandrano |  | 2020-08-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | AMM | Manandriana | Anjoman'Ankona | Anjoman'Ankona | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | DREAH | En attente de la remise de l'offre |  | En cours |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | HTM | Ambalavao | Ambohimandroso | Ambohimandroso | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2020-07-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | HTM | Ambalavao | Andrainjato | Andrainjato | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-07-01 | 2020-09-30 | 2021-04-22 | 17-18-19 aout 2021 | Clôturé | En cours | 2021-10-28 | 2021-10-28 | 100% | 2022-02-02 | 2022-03-09 | - |  | - | - | - | - | [13 empty] | Attente RD | -
CARE | HTM | Ambalavao | Besoa | Besoa | Manifestation spontanée | ESF- LAKAY - Ambassade d'Allemagne | AEPG (BS, BP, PEC) | DREAH | LAKAY | 2020-09-01 | 2022-02-15 |  |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | HTM | Ambalavao | Namoly | Namoly | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Miharintsoa |  | En cours |  | Attente remise des offres | #N/A | En cours | - | En cours | 0% | - | - | - |  | - | - | - | - | [13 empty] | En cours | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | HTM | Ambalavao | Sendrisoa | Sendrisoa | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Miharintsoa |  | 2021-09-26 |  | Attente remise des offres | #N/A | En cours | - | En cours | 0% | - | - | - |  | - | - | - | - | [13 empty] | En cours | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | HTM | Lalangina | Ambalamahasoa | Ambalamahasoa | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-05-01 | 2020-12-01 | 2021-09-20 | 13-14-15 juillet 2021 | Clôturé | - | 2022-04-07 | 2022-04-07 | 100% | 2022-07-23 | - | - |  | - | - | - | - | [13 empty] | RP et RD | -
CARE | HTM | Lalangina | Ambatolahy Vohidravina | Ambatolahy Vohidravina | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  |  | 2020-09-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | HTM | Lalangina | Andrainjato Est | Andrainjato Est | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | SECOA | 2020-06-01 | 2020-08-28 | 2021-08-11 | 18-19-20-21-22 septembre 2020 | Clôturé | - | 2021-09-22 | 2021-09-22 | 100% | 2022-01-31 | 2022-03-19 | - |  | - | - | - | - | [13 empty] | Attente RD | -
CARE | HTM | Lalangina | Androy | Androy | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-06-01 | 2020-08-26 | 2021-02-22 | 16-17-18 septembre 2020 | Clôturé | - | 2021-07-09 | 2021-07-09 | 100% | 2021-10-15 | 2021-10-25 | - |  | - | - | - | - | [13 empty] | Attente RD | -
CARE | HTM | Vohibato | Andranomiditra | Andranomiditra | Manifestation spontanée | MICKAEL | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-06-01 | 2020-07-31 | 2020-10-23 | 2021-12-01 | Clôturé | En cours | - | En cours | 0% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
CARE | HTM | Vohibato | Andranovorivato | Andranovorivato | Dotation de matériel | Zanak'Ampielezana | AEPG (BS, BP, PEC) | DREAH | LAZA |  | 2022-01-18 |  |  | #N/A | - | 2022-03-11 | 2022-03-11 | 95% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
CARE | HTM | Vohibato | Andranovorivato | Andranovorivato | Dotation de matériel | Ambassade d'Allemagne - LAZA | AEPG (BS, BP, PEC) | DREAH | LAZA |  | 2021-12-10 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | HTM | Vohibato | Ankaromalaza | Ankaromalaza Mifanasoa | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2020-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | HTM | Vohibato | Fandrandava | Fandrandava | Autre financement | TANY MEVA | AEPP (BS, BP, PEC) | DREAH |  | 2020-07-01 | En cours |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | HTM | Vohibato | Ihazoara | Ihazoara | Manifestation spontanée | MICKAEL | AEPG (BS, BP, PEC) | DREAH | Mickael |  | En cours |  | 2021-12-01 | Clôturé | En cours | - | En cours | 0% | - | - | - |  | - | - | - | - | [13 empty] | En cours
CARE | HTM | Vohibato | Maneva | Maneva | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2020-09-01 | 2020-10-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | HTM | Vohibato | Vinanitelo | Vinanitelo | Autre financement | EAU'RIZON | AEPG (BS, BP, PEC) | Bushproof |  | 2020-09-26 | 2020-10-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | V7V | Ifanadiana | Ambiabe | Ambiabe | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-07-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Ifanadiana | Androrangavola | Androrangavola | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  |  | 2020-12-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Ifanadiana | Antaretra | Antaretra | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2019-06-01 | 2019-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-03-03 | 2020-04-03 |  |  | - | - | 2020-07-30 | - | [13 empty] | Attente RD | -
CARE | V7V | Ifanadiana | Kelilalina | Kelilalina | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | DREAH | Fitahiana |  | 2019-02-01 |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Site foire en cours de mise à jour de l'étude et en attente de la remise de l'offre
CARE | V7V | Ifanadiana | Kelilalina | Kianjanomby | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2018-03-01 | 2018-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-16 | 2019-09-23 | 2020-09-28 |  | - | - | 2020-07-30 | - | [13 empty] | Exploitation | -
CARE | V7V | Ifanadiana | Tsaratanana | Tsaratanana | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-06-01 | 2020-11-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Ikongo | Ambatofotsy | Ambalatenina | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2018-11-01 | 2018-07-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-07-04 | 2019-09-25 | 2020-09-29 |  | - | - | 2020-07-30 | - | [13 empty] | Exploitation | -
CARE | V7V | Ikongo | Ambatofotsy | Ambatofotsy | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2018-11-01 | 2018-07-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-07-04 | 2019-09-25 | 2020-09-29 |  | - | - | 2020-07-30 | - | [13 empty] | Exploitation | -
CARE | V7V | Ikongo | Ambatofotsy | Ambodiara sakorihy | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2018-07-01 | 2018-07-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-07-04 | 2019-09-25 | 2020-09-29 |  | - | - | 2020-07-30 | - | [13 empty] | Exploitation | -
CARE | V7V | Ikongo | Ambatofotsy | Tsarakianja | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Ikongo | Ambinantromby | Ambinantromby | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-10-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Ikongo | Manampatrana | Manampatrana | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2018-11-01 | 2019-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-03-06 | 2020-04-02 | 2020-09-29 |  | - | - | 2020-07-30 | - | [13 empty] | Exploitation | -
CARE | V7V | Ikongo | Maromiandra | Maromiandra | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-06-01 | 2019-11-01 | 2020-07-22 |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Ikongo | Tolongoina | Tolongoina | PPP | USAID | AEPG (BS, BP, PEC) | DREAH | Bushproof | 2018-04-01 | 2018-05-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Manakara Atsimo | Agnorombato | Agnorombato | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-06-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Manakara Atsimo | Amboanjo | Amboanjo | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-06-01 | 2019-11-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Manakara Atsimo | Ambotaka | Ambotaka | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Manakara Atsimo | Ampasimanjeva | Ampasimanjeva | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | EC ABRAHAM | 2020-09-01 | 2021-05-01 | 2022-04-27 | 2021-07-19 | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Manakara Atsimo | Analavory | Analavory | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-09-01 |  |  |  |  | - | - | - | 5% | 2022-08-31 | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Manakara Atsimo | Fenomby | Fenomby | PPP | AFD | AEPG (BS, BP, PEC) | Bushproof | Fitahiana | 2020-09-01 | 2020-12-01 | #N/A | 2021-03-04 | Clôturé | 2021-06-15 | 2021-06-15 | 2021-06-21 | 100% | 2021-09-21 | 2021-09-27 | - |  | 2022-04-13 | - | - | - | [13 empty] | Attente RD | -
CARE | V7V | Manakara Atsimo | Marofarihy | Marofarihy | PPP | USAID | AEPP (BS, BP, PEC) |  |  |  | 2019-11-01 | 2020-07-10 |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Manakara Atsimo | Vohimasina Nord | Vohimasina Nord | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | Fitahiana |  | 2021-06-01 | En cours | 2021-07-26 | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Mananjary | Andonabe | Andonabe | PPP | AFD | AEPG (BS, BP, PEC) | Sandandrano | Ecowin | 2020-10-01 | 2021-02-01 | #N/A | 2021-03-24 | Clôturé | 2021-08-17 | 2021-09-13 | 2021-09-13 | 100% | 2022-05-04 | 2022-06-23 | - |  | 2022-03-08 | - | - | - | [13 empty] | Attente RD | -
CARE | V7V | Mananjary | Namorona | Namorona | PPP | Privé | AEPP (BS, BP, PEC) | Bushproof | Fitahiana | 2020-09-01 | 2021-01-18 | #N/A | 2021-08-16 | Clôturé | 2022-03-18 | 2022-03-28 | 2022-03-25 | 65% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
CARE | V7V | Vohipeno | Ambohitrova | Ambohitrova | PPP+ | USAID | AEPP (BS, BP, PEC) | DREAH | Mickael |  | #N/A | #N/A | #N/A | #N/A | - | 2020-08-18 | - | 100% | 2021-06-16 | 2021-07-07 | - |  | - | - | - | - | [13 empty] | Attente RD | -
CARE | V7V | Vohipeno | Andemaka | Andemaka | PPP | USAID | AEPP (BS, BP, PEC) | DREAH | Bushproof | 2018-03-01 | 2018-04-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-18 | 2019-09-27 | 2020-09-29 |  | - | - | 2020-11-24 | - | [13 empty] | Exploitation | -
CARE | V7V | Vohipeno | Ankarimbary | Ankarimbary | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2019-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Vohipeno | Anoloka | Lazamasy | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2019-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Vohipeno | Ilakatra | Ilakatra | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-08-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Vohipeno | Lokomby | Lokomby | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | Mickael |  | 2019-12-01 | Validé |  | Clôturé | - | 2020-08-18 | - | 100% | 2020-09-23 | 2020-09-28 | 2022-09-02 |  | - | - | 2020-11-24 | - | [13 empty] | Exploitation | -
CARE | V7V | Vohipeno | Mahabo | Mahabo | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2019-06-01 | 2019-11-01 | 2020-07-13 |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Vohipeno | Mahasoabe | Mahasoabe | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2019-06-01 | 2019-11-01 | Validé |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Vohipeno | Mahazoarivo | Mahazoarivo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2020-10-01 | 2021-02-01 | 2021-11-16 | 2021-07-12 | Clôturé | - | - | 2022-04-21 | 40.25% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
CARE | V7V | Vohipeno | Nato | Nato | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2019-08-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Vohipeno | Savana | Savana | PPP | USAID | AEPP (BS, BP, PEC) | BushProof |  | 2019-08-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CARE | V7V | Vohipeno | Vohitrindry | Vohitrindry | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | EC ABRAHAM | 2018-03-01 | 2019-11-01 | 2021-05-25 | 2020-12-07 | Clôturé | 2021-09-13 | 2021-09-22 | 2021-09-20 | 100% | 2022-01-13 | 2022-09-01 | - |  | 2022-03-21 | - | - | - | [13 empty] | Attente RD | -
CRS | ATS | Brickaville | Ambohimanana | Ambohimanana | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2018-03-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Brickaville | Ampasimbe | Ampasimbe | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Sandandrano | 2ADH | 2019-10-01 |  |  |  | #N/A | En cours | - | - | - | - | - | - |  | - | - | - | - | [13 empty] | En cours | Financement Prive et CR + Dotation conduite et kiosque
CRS | ATS | Brickaville | Andekaleka | Andekaleka | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | #N/A |  |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Brickaville | Andovoranto | Ambila Lemaitso | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | AΠR |  | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-02-13 | 2019-04-10 | 2019-08-10 |  | - | - | 2020-03-03 | - | [13 empty] | Exploitation | -
CRS | ATS | Brickaville | Andovoranto | Andovoranto | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2018-03-01 | 2020-01-31 | 2020-05-27 |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Brickaville | Fetraomby | Fetraomby | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | SEDERA |  |  |  |  | #N/A | OK | - | - | 70% | - | - | - |  | - | - | - | - | [13 empty] | En cours | Financement prive + Dotation conduite et kiosque
CRS | ATS | Brickaville | Mahatsara | Mahatsara | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | 2 ADH | 2019-05-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-05-09 | 2020-08-25 | 2021-08-13 |  | - | - | 2020-11-24 | - | [13 empty] | Exploitation | -
CRS | ATS | Brickaville | Mahatsara | Maromby | PPP+ | USAID | AEPP (BS, BP, PEC) | Zara-Rano | 2 ADH |  | 2021-02-20 | Validé |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Brickaville | Ranomafana Est | Antongobato | PPP+ | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | LOVA VELU | 2018-11-01 | 2020-01-31 | 2020-05-27 |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Brickaville | Ranomafana Est | Marovola | PPP+ | USAID | AEPG (BS, BP, PEC) | Bushproof | LOVA VELU |  | 2021-11-15 | En cours |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Brickaville | Ranomafana Est | Ranomafana Est | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | LOVA VELU | 2018-03-01 | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-16 | 2019-06-22 | 2020-08-10 |  | - | - | 2020-03-03 | - | [13 empty] | Exploitation | -
CRS | ATS | Brickaville | Razanaka | Razanaka | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Sandandrano | LOVA VELU | 2019-10-01 |  |  |  | #N/A | En cours | - | - | - | - | - | - |  | - | - | - | - | [13 empty] | En cours | Financement prive + Dotation conduite et kiosque
CRS | ATS | Toamasina II | Ambinaninony | Ambodisovoka | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2018-03-01 | 2018-04-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Ambodilazana | Ambodilazana | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2018-03-01 |  |  |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Ambodilazana | Ambodimanga Volobe | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2018-06-01 |  |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Ambodilazana | Amboditeza | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  |  | 2018-04-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Ambodiriana | Ambodiriana | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2019-06-01 | 2020-03-01 | #N/A |  | Clôturé | 2020-07-03 | - | 2020-07-23 | 100% | 2020-11-09 | 2020-12-09 | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Ambodiriana | Analamangahazo | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2019-06-01 | 2020-03-01 | #N/A |  | Clôturé | 2020-07-03 | - | 2020-07-23 | 100% | 2020-11-10 | 2020-12-10 | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Ambodiriana | Fontsimavo | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2019-06-01 | 2020-03-01 | #N/A |  | Clôturé | 2020-07-03 | - | 2020-07-22 | 100% | 2020-11-10 | 2020-12-09 | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Amboditandroroho | Amboakarivo | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | EATC |  | 2019-10-01 | #N/A |  | Clôturé | 2020-01-22 | - | 2020-01-21 | 100% | 2020-09-12 | 2020-09-16 | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Amboditandroroho | Amboditandroroho | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | EATC |  | 2019-10-01 | #N/A |  | Clôturé | 2020-01-22 | - | 2020-01-20 | 100% | 2020-09-11 | 2020-09-15 | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Amboditandroroho | Mahatsara | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | EATC |  | 2019-10-01 | #N/A |  | Clôturé | 2020-01-22 | - | 2020-01-21 | 100% | 2020-09-10 | 2020-09-16 | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Ampasimadinika | Ampasimadinika | PPP | USAID | AEPP (BS, BP, PEC) | Sandandrano | 2 ADH | 2019-06-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-08-22 | 2020-08-24 | 2021-08-13 |  | - | - | 2020-11-24 | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Ampasimbe Onibe | Ampasimbe Onibe | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | CREAT BTP | 2018-03-01 | 2018-04-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-30 | 2019-06-21 | 2020-08-29 |  | - | - | 2020-03-03 | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Andondabe | Andondabe | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | NMS | 2018-07-01 |  |  |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Andranobolahy | Andranobolahy | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Sandandrano | #N/A | 2019-10-01 |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Fanandrana | Fanandrana | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | NMS | 2019-10-01 | 2020-02-01 | #N/A | 2020-02-01 | Clôturé | 2020-04-10 | 2020-03-19 | 2020-05-05 | 100% | 2020-11-05 | Done | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Mahavelona Foulpointe | Ambohimanarivo | PPP+ | USAID | AEPG (BS, BP, PEC) | Bushproof | Sandandrano |  | 2021-11-15 | Validé |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Mahavelona Foulpointe | Bongabe | PPP+ | USAID | AEPG (BS, BP, PEC) | DREAH | Sandandrano | 2018-11-01 | 2021-11-15 | Validé |  | #N/A | En cours | - | - | - | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
CRS | ATS | Toamasina II | Mahavelona Foulpointe | Mahavelona-Foulpointe | PPP | USAID | AEPP (BS, BP, PEC) | DREAH | Sandandrano |  | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-02-11 | 2019-04-09 | 2020-08-07 |  | - | - | 2021-09-20 | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Mahavelona Foulpointe | Marofarihy | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-03-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Toamasina II | Sahambala | Ambalakondro | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2019-08-01 | #N/A |  | Clôturé | 2019-12-10 | 2019-12-10 | 2019-12-17 | 100% | 2020-03-18 | Done | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Ambodirafia | PPP+ | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2020-02-01 | #N/A |  | Clôturé | 2020-05-05 | - | - | 100% | 2020-10-15 | Done | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Maroangivy | PPP+ | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2020-02-01 | #N/A |  | Clôturé | 2020-05-05 | - | - | 100% | 2020-10-14 | Done | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Sahambala | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2019-08-01 | #N/A |  | Clôturé | 2019-12-10 | 2019-12-10 | 2019-12-17 | 100% | 2020-03-17 | Done | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Sahavongo | PPP+ | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2020-02-01 | #N/A |  | Clôturé | 2020-05-05 | - | - | 100% | 2020-10-16 | Done | Done |  | - | - | - | - | [13 empty] | Exploitation | -
CRS | ATS | Vatomandry | Ambalavolo | Ambalavolo | Manifestation spontanée | Privé | AEPP (BS, BP, PEC) | Bushproof | #N/A | 2019-07-01 |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Ambalavolo | Tanandava | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Bushproof | #N/A | 2019-07-01 |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Amboditavolo | Amboditavolo | Manifestation spontanée | Privé | AEPP (BS, BP, PEC) | Bushproof |  | 2019-07-01 |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Ambodivoananto | Marosampanana | Manifestation spontanée | Privé | AEPP (BS, BP, PEC) | DREAH | #N/A |  |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Ambodivoananto | Tamboro | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Bushproof | #N/A | 2019-06-01 |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Ampasimadinika | Ampasimadinika | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2018-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Antanambao Mahatsara | Antanambao Mahatsara | Manifestation spontanée | Privé | AEPP (BS, BP, PEC) | DREAH | #N/A |  |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Iamborano | Iamborano | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-08-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Ilaka Est | Ilaka-Est | PPP | USAID | AEPP (BS, BP, PEC) | Sandandrano | LOVA VELU |  | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-02-06 | 2019-04-11 | 2020-08-12 |  | - | - | 2020-03-03 | - | [13 empty] | Exploitation | -
CRS | ATS | Vatomandry | Maintinandry | Maintinandry | Manifestation spontanée | Privé | AEPP (BS, BP, PEC) | DREAH | #N/A |  |  |  |  | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Niarovana Caroline | Niarovana Caroline | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | 2 ADH | 2018-03-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-01-22 | 2020-05-09 | 2021-08-14 |  | - | - | 2020-11-24 | - | [13 empty] | Exploitation | -
CRS | ATS | Vatomandry | Niherenana | Niherenana | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2019-06-01 |  |  |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Sahamatevina | Sahamatevina | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2019-06-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Tanambao Vahatrakaka | Tanambao Vahatrakaka | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2019-08-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | ATS | Vatomandry | Tsarasambo | Tsarasambo | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | LOVA VELU | 2018-03-01 | 2019-11-01 |  |  | Clôturé | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | VKN | Antanifotsy | Ambatotsipihina | Ambatotsipihina | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | #N/A | 2021-02-01 | 2021-08-04 | 2022-03-16 | 2022-01-10 | En cours | En cours | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | VKN | Antanifotsy | Ambohimandroso | Ambohimandroso | Dotation de matériel | USAID | AEPG (BS, BP, PEC) | Sandandrano | FANOVOZANTSOA | 2021-02-01 | En cours | - | - | #N/A | - | - | - | - | - | - | - |  | - | - | - | - | [6 empty] | 33.925 | 21.6475 |  | 18.48 |  |  |  |  | -
CRS | VKN | Antanifotsy | Antanifotsy | Antanifotsy | Dotation de matériel | USAID | AEPP (BS, BP, PEC) | DREAH | JIRAMA | #N/A | 2021-02-18 | #N/A | #N/A | #N/A | En cours | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | VKN | Antsirabe II | Ambohitsimanova | Ambohitsimanova | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | ACOGEMA | 2020-02-01 | 2020-06-30 | 2021-01-19 | 2020-09-15 | Clôturé | 2021-04-06 | 2021-05-07 | 2021-05-27 | 100% | 2021-08-23 | 2021-10-29 | 2022-06-23 |  | 2021-10-14 | 2021-10-14 | - | - | [13 empty] | Exploitation | -
CRS | VKN | Antsirabe II | Andranomanelatra | Andranomanelatra | Dotation de matériel | USAID | AEPG (BS, BP, PEC) | DREAH | SRAFI RANOVELONA | #N/A | 2021-02-11 | #N/A | #N/A | #N/A | En cours | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
CRS | VKN | Antsirabe II | Antsoatany | Antsoatany | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | 2 ADH | 2020-02-01 | 2020-06-30 | 2021-01-06 | 2020-09-15 | Clôturé | 2021-04-06 | 2021-05-07 | 2021-05-30 | 100% | 2021-12-14 | 2022-01-14 | 2022-06-24 |  | 2021-10-15 | 2021-10-15 | - | - | [7 empty] | 104 | [5 empty] | Exploitation | -
CRS | VKN | Antsirabe II | Soanindrariny | Soanindrariny | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | EC ABRAHAM | 2020-02-01 | 2020-06-30 | 2021-01-11 | 2020-09-15 | Clôturé | 2021-04-06 | 2021-05-07 | 2021-06-01 | 100% | 2021-10-28 | 2021-11-23 | 2022-06-23 |  | 2021-10-15 | 2021-10-15 | - | - | [6 empty] | 7900 | [6 empty] | Exploitation | -
CRS | VKN | Betafo | Alakamisy Anativato |  | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano | [5 empty] | En cours | - | - | - | - | - | - | [18 empty] | En cours
CRS | VKN | Betafo | Ambohimanambola | Ambohimanambola | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | #N/A | #N/A | 2021-07-17 | Validé | 2022-01-10 | En cours | - | - | - | - | - | - | - |  | - | - | - | - |  |  |  |  | 57 | [9 empty] | -
CRS | VKN | Betafo | Mandritsara |  | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano | [5 empty] | En cours | - | - | - | - | - | - | [18 empty] | En cours
CRS | VKN | Betafo | Soavina |  | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano | [5 empty] | En cours | - | - | - | - | - | - | [18 empty] | En cours
WaterAid | ALMA | Ambatondrazaka | Ambohitsilaozana | Ambohitsilaozana | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Ambatondrazaka | Amparihintsokatra | Amparihintsokatra | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-11-01 | 2020-10-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Ambatondrazaka | Andilanatoby | Andilanatoby | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-07-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Ambatondrazaka | Bejofo | Bejofo | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-07-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Ambatondrazaka | Imerimandroso | Imerimandroso | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2019-11-01 | 2020-11-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Amparafaravola | Ambohijanahary | Ambohijanahary | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof |  | 2020-12-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Rano an'ala B saika handray azy, mbola miantona eo @ geotechnique
WaterAid | ALMA | Amparafaravola | Ambohitrarivo | Ambohitrarivo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2019-12-01 | 2020-10-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | LOVA VELU efa nanao restitution fa miandry contribution commune, miandry reunion de negociation
WaterAid | ALMA | Amparafaravola | Amparafaravola | Amboavory | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | DREAH |  |  |  | N/A |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Financement: ICG, USAID, Commune, autres partenaires
WaterAid | ALMA | Amparafaravola | Amparafaravola | Ambongabe | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | EGC Tamby | 2018-11-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-09-11 | 2020-09-15 |  |  | - | - | 2020-07-30 | - | 190 |  |  | 81 | [5 empty] | 16.05 |  |  |  | Attente RD | Systeme Ambongabe - Betatamo
WaterAid | ALMA | Amparafaravola | Amparafaravola | Ampilahoana | PPP+ | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Amparafaravola | Amparafaravola | Andilana Atsimo | Foire (GC to GP) | Privé | AEPG (BS, BP, PEC) | DREAH | Rano an'ala B | [5 empty] | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Mbola miantona, miandry resiliation
WaterAid | ALMA | Amparafaravola | Amparafaravola | Antsakoana | PPP+ | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Amparafaravola | Amparafaravola | Betatamo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | EGC Tamby | 2018-11-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-09-11 | 2020-09-15 |  |  | - | - | 2020-07-30 | - | 35 |  |  |  | 56400 |  | 10.3 |  |  | 3.7 |  |  |  | Attente RD | Systeme Ambongabe - Betatamo
WaterAid | ALMA | Amparafaravola | Antanambe | Amborompotsy | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Amparafaravola | Antanambe | Antanambe | Dotation de matériel | Sedera | AEPG (BS, BP, PEC) | DREAH | SEDERA | [5 empty] | - | - | Attente dotation | - | - | - | - |  | - | - | - | - | [14 empty] | Efa talohan'ny tetikasa, efa + 5ans ny SEDERA no nitantana tao, miandry restitution an'ny Ese SEDERA
WaterAid | ALMA | Amparafaravola | Morarano Chrome | Morarano Chrome | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | LOVA VELU | 2019-09-01 | 2020-01-31 | 2020-11-18 |  | Clôturé | - | - | - | 100% | 2021-10-27 | - | - |  | 9 Juin 2021 | 9 Juin 2021 | - | - | [13 empty] | RP et RD | Natao ny RT voalohany dia natao visite tech fa tsy nandeha ny rano, Nisy extension natao dia hiandrasana an'io ny RP
WaterAid | ALMA | Moramanga | Amboasary | Amboasary | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano |  | En cours |  |  |  | OK | - | - | - | - | - | - |  | - | - | - | - | [13 empty] | En cours | Natureau, LOVA VELU no nametraka offre, miandry valiny CAO
WaterAid | ALMA | Moramanga | Ambohibary | Ambohibary | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Moramanga | Ambohidronono | Ambohidronono | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Moramanga | Andaingo | Andaingo | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Rano an'ala B | 2019-11-01 | En cours |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | Financement: Commune, Naturano, Fanamby, USAID
WaterAid | ALMA | Moramanga | Andasibe | Andasibe | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-03-01 | 2018-08-01 |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Moramanga | Anosibe Ifody | Ambodinifody | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Rano an'ala B | 2018-11-01 | 2019-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-12-20 | 2020-09-09 | 2020-09-09 |  | - | - | 2020-03-18 | - | [13 empty] | Exploitation | -
WaterAid | ALMA | Moramanga | Anosibe Ifody | Ankarefo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  |  | 2020-03-01 |  |  |  | - | - | - | - | - | - | -
WaterAid | ALMA | Moramanga | Anosibe Ifody | Tsarafasina | Dotation de matériel | USAID | AEPG (BS, BP, PEC) | DREAH | Rano an'ala B | [5 empty] | - | - | 2022-04-14 | 60% | - | - | - |  | - | - | - | - | [13 empty] | En cours | Addendum signé en 2021
WaterAid | ALMA | Moramanga | Antaniditra | Antaniditra | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2019-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Moramanga | Beforona | Ambinanisoavolo | PPP+ | USAID | AEPG (BS, BP, PEC) | DREAH | ACOGEMA | [5 empty] | - | - | 2022-04-05 | 50% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
WaterAid | ALMA | Moramanga | Beforona | Beforona | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | ACOGEMA | 2018-03-01 | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-01-24 | 2019-07-06 | 2020-09-08 |  | - | - | 2019-08-02 | - | 18 | 3.9 |  |  |  |  | 2.75 |  | 27 | 3.7 |  | 2800 | 165 | Exploitation | -
WaterAid | ALMA | Moramanga | Beforona | Marolafa | PPP+ | USAID | AEPG (BS, BP, PEC) | DREAH | ACOGEMA | [5 empty] | - | - | 2022-04-05 | 80% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
WaterAid | ALMA | Moramanga | Beforona | Marozevo/Soakambana | PPP+ | USAID | AEPG (BS, BP, PEC) | DREAH | ACOGEMA | [5 empty] | - | - | 2022-04-05 | 80% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
WaterAid | ALMA | Moramanga | Belavabary | Belavabary | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Moramanga | Belavabary | Marovitsika | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano |  | 2018-11-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Moramanga | Lakato | Lakato | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof |  | 2019-09-01 |  |  |  |  | - | - | - | - | - | - | - |  | - | - | - | - | [14 empty] | -
WaterAid | ALMA | Moramanga | Mandialaza | Mandialaza | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Sandandrano | Rano an'ala B | 2019-09-01 | En cours |  |  |  | 11 Mars 2022 | - | Attente accord environnemental | - | - | - | - |  | 11 Mars 2022 | 11 Mars 2022 | - | - | [13 empty] | En cours | Financement: Commune, RANO An'ALA B, Fanamby, USAID
WaterAid | ALMA | Moramanga | Morarano Gara | Morarano Gara | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Rano an'ala B | 2018-11-01 | 2020-11-11 | 2021-08-23 |  |  | - | - | 2022-05-25 | 73.98% | - | - | - |  | - | - | - | - | [13 empty] | En cours | -
WaterAid | ALMA | Ambatondrazaka | Ambatosoratra | Ambatosoratra | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Rano an'ala B | [5 empty] | En cours | [24 empty] | En cours
WaterAid | ALMA | Moramanga | Sabotsy Anjiro | Sabotsy Anjiro | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | RPIJ | 2018-11-01 | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2018-12-18 | 2019-07-05 | 2020-09-08 |  | - | - | 2019-08-02 | - | [13 empty] | Exploitation | -
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD en cours de mise à jour par les soumissionnaires foires
Note on Y7: HP: Mbola tsy nanao retour i Sandandano amin'ny feedbackn'ireo contrat ireo,eny hatramin'ny an'i Ilak Centre
Note on L11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD en cours de mise à jour par les soumissionnaires foires
Note on L40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par BP en Fevrier 2019
Note on K43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par BP en Juillet 2018 APS fait par SDN en Novembre 2018
Note on L43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par BP en Juillet 2018
Note on K44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par BP en Juillet 2018 APS fait par SDN en Novembre 2018
Note on L44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par BP en Juillet 2018
Note on K46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par BP en Juillet 2018 APS fait par SDN en Novembre 2018
Note on K47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par SDN en Novembre 2018
Note on L72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Existence version Novembre 2019 et une nouvelle version en Septembre 2020 fait par BP
Note on G77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Sandandrano
Note on L77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par Sandandrano en Novembre 2019
Note on G81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Sandandrano
Note on L81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par Sandandrano en Decembre 2019
Note on G86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Sandandrano
Note on L102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par Sandandrano
Note on G104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof en Mars 2018
Note on G120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Sandandrano
Note on P126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Convention entre JIRAMA - CRS - Commune - MEAH
Note on P128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Convention entre SRAFI RANOVELONA - CRS - Commune - MEAH - (HOLCIM)
Note on C135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Foire
Note on C136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Foire
Note on C137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Foire
Note on C138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Foire
Note on C139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Foire

## Site actuel
Organisation | Région | District | Commune | Site | Stratégie | Financement | Système | Maître d'œuvre | Entreprise | APS vf le | APD vf le | ESF validé le | Analyse et Dépouillement | AOR | Contrat signé le | OS | Démarrage travaux le | Avancement travaux | RT | RP | RD | Situation | Observations
CARE | AMM | Ambositra | Ilaka Centre | Ilaka Centre | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | AΠR | 2020-06-01 | 2020-09-30 | 2021-07-22 | 2021-07-01 | Clôturé | 2022-03-18 | 2022-03-30 | 2022-03-31 | 100% | 2022-08-25 | 2022-10-13 | 2023-04-26 | Attente RD | -
CARE | AMM | Ambositra | Ivato | Ivato Centre | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | AΠR | 2020-06-01 | 2020-09-30 | 2021-11-16 | 2021-07-12 | Clôturé | 2021-09-13 | 2021-09-22 | 2021-09-22 | 100% | 2021-12-17 | 2022-01-31 | 2022-08-09 | Exploitation | -
CARE | AMM | Manandriana | Ambatomarina | Ambatomarina | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | ACOGEMA | 2020-07-01 | 2020-09-30 | 2021-06-29 | 2021-08-01 | Clôturé | 2021-10-12 | 2021-10-22 | 2021-10-22 | 100% | 2022-02-04 | 2022-02-19 | 2022-09-15 | Exploitation | -
CARE | HTM | Ambalavao | Andrainjato | Andrainjato | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-07-01 | 2020-09-30 | 2021-04-22 | 17-18-19 aout 2021 | Clôturé | En cours | 2021-10-28 | 2021-10-28 | 100% | 2022-02-02 | 2022-03-09 | 2022-09-30 | Exploitation | -
CARE | HTM | Ambalavao | Namoly | Namoly | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Miharintsoa |  | En cours |  | Attente remise des offres | #N/A | En cours | - | 2022-09-16 | 10% | 2022-11-30 | 2022-12-23 | 2022-12-23 | En cours | -
CARE | HTM | Ambalavao | Sendrisoa | Sendrisoa | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Miharintsoa |  | 2021-09-26 |  | Attente remise des offres | #N/A | En cours | - | 2022-09-15 | 10% | 2022-11-30 | 2022-12-23 | 2022-12-23 | En cours | -
CARE | HTM | Lalangina | Ambalamahasoa | Ambalamahasoa | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-05-01 | 2020-12-01 | 2021-09-20 | 13-14-15 juillet 2021 | Clôturé | - | 2022-04-07 | 2022-04-07 | 100% | 2022-07-23 | 2022-09-12 | 2022-12-23 | Attente RD | -
CARE | HTM | Lalangina | Andrainjato Est | Andrainjato Est | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | SECOA | 2020-06-01 | 2020-08-28 | 2021-08-11 | 18-19-20-21-22 septembre 2020 | Clôturé | - | 2021-09-22 | 2021-09-22 | 100% | 2022-01-31 | 2022-03-19 | 2022-09-29 | Exploitation | -
CARE | HTM | Lalangina | Androy | Androy | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-06-01 | 2020-08-26 | 2021-02-22 | 16-17-18 septembre 2020 | Clôturé | - | 2021-07-09 | 2021-07-09 | 100% | 2021-10-15 | 2021-10-25 | 2022-09-19 | Exploitation | -
CARE | HTM | Vohibato | Andranomiditra | Andranomiditra | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2020-06-01 | 2020-07-31 | 2020-10-23 | 2021-12-01 | Clôturé | En cours | - | 2022-09-13 | 10% | 2022-11-30 | 2022-12-23 | 2022-12-23 | En cours | -
CARE | HTM | Vohibato | Andranovorivato | Andranovorivato | Dotation de matériel | Zanak'Ampielezana | AEPG (BS, BP, PEC) | DREAH | LAZA |  | 2022-01-18 |  |  | #N/A | - | 2022-03-11 | 2022-03-11 | 95% | 2022-11-01 | 2022-12-01 | 2022-12-01 | En cours | -
CARE | HTM | Vohibato | Ihazoara | Ihazoara | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Mickael |  | En cours |  | 2021-12-01 | Clôturé | En cours | - | 2022-09-14 | 10% | 2022-11-30 | 2022-12-23 | 2022-12-23 | En cours
CARE | V7V | Ifanadiana | Antaretra | Antaretra | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2019-06-01 | 2019-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-03-03 | 2020-04-03 | 2021-06-15 | Exploitation | -
CARE | V7V | Ifanadiana | Kelilalina | Kianjanomby | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2018-03-01 | 2018-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-16 | 2019-09-23 | 2020-09-28 | Exploitation | -
CARE | V7V | Ikongo | Ambatofotsy | Ambalatenina | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2018-11-01 | 2018-07-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-07-04 | 2019-09-25 | 2020-09-29 | Exploitation | -
CARE | V7V | Ikongo | Ambatofotsy | Ambatofotsy | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2018-11-01 | 2018-07-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-07-04 | 2019-09-25 | 2020-09-29 | Exploitation | -
CARE | V7V | Ikongo | Ambatofotsy | Ambodiara sakorihy | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | Mickael | 2018-07-01 | 2018-07-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-07-04 | 2019-09-25 | 2020-09-29 | Exploitation | -
CARE | V7V | Ikongo | Manampatrana | Manampatrana | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2018-11-01 | 2019-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-03-06 | 2020-04-02 | 2020-09-29 | Exploitation | -
CARE | V7V | Manakara Atsimo | Ampasimanjeva | Ampasimanjeva | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | EC ABRAHAM | 2020-09-01 | 2021-05-01 | 2022-04-27 | 2021-07-19 | Clôturé | - | - | 2022-08-31 | 8% | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours | -
CARE | V7V | Manakara Atsimo | Fenomby | Fenomby | PPP | AFD | AEPG (BS, BP, PEC) | Bushproof | Fitahiana | 2020-09-01 | 2020-12-01 | #N/A | 2021-03-04 | Clôturé | 2021-06-15 | 2021-06-15 | 2021-06-21 | 100% | 2021-09-21 | 2021-09-27 | 2022-12-22 12:00 | Attente RD | -
CARE | V7V | Manakara Atsimo | Vohimasina Nord | Vohimasina Nord | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | Fitahiana |  | 2021-06-01 | Validé | 2021-07-26 | Clôturé | - | - | 2022-09-16 | 5% | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours | -
CARE | V7V | Mananjary | Andonabe | Andonabe | PPP | AFD | AEPG (BS, BP, PEC) | Sandandrano | Ecowin | 2020-10-01 | 2021-02-01 | #N/A | 2021-03-24 | Clôturé | 2021-08-17 | 2021-09-13 | 2021-09-13 | 100% | 2022-05-04 | 2022-06-23 | 2022-12-22 12:00 | Attente RD | -
CARE | V7V | Mananjary | Namorona | Namorona | PPP | Privé | AEPP (BS, BP, PEC) | Bushproof | Fitahiana | 2020-09-01 | 2021-01-18 | #N/A | 2021-08-16 | Clôturé | 2022-03-18 | 2022-03-28 | 2022-03-25 | 73% | 2022-11-30 | 2022-12-23 | 2022-12-23 | En cours | -
CARE | V7V | Vohipeno | Ambohitrova | Ambohitrova | PPP+ | Privé | AEPP (BS, BP, PEC) | DREAH | Mickael |  | #N/A | #N/A | #N/A | #N/A | - | 2020-08-18 | - | 100% | 2021-06-16 | 2021-07-07 | 2022-09-02 | Exploitation | -
CARE | V7V | Vohipeno | Andemaka | Andemaka | PPP | USAID | AEPP (BS, BP, PEC) | DREAH | Bushproof | 2018-03-01 | 2018-04-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-18 | 2019-09-27 | 2020-09-29 | Exploitation | -
CARE | V7V | Vohipeno | Lokomby | Lokomby | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | Mickael |  | 2019-12-01 | Validé |  | Clôturé | - | 2020-08-18 | - | 100% | 2020-09-23 | 2020-09-28 | 2022-09-02 | Exploitation | -
CARE | V7V | Vohipeno | Mahazoarivo | Mahazoarivo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Mickael | 2020-10-01 | 2021-02-01 | 2021-11-16 | 2021-07-12 | Clôturé | - | - | 2022-04-21 | 68.31% | 2022-10-31 | 2022-11-15 | 2023-05-29 | En cours | -
CARE | V7V | Vohipeno | Vohitrindry | Vohitrindry | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | EC ABRAHAM | 2018-03-01 | 2019-11-01 | 2021-05-25 | 2020-12-07 | Clôturé | 2021-09-13 | 2021-09-22 | 2021-09-20 | 100% | 2022-01-13 | 2022-09-01 | 2023-03-15 | Attente RD | -
CRS | ATS | Brickaville | Ampasimbe | Ampasimbe | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Sandandrano | 2ADH | 2019-10-01 |  |  |  | #N/A | En cours | - | - | - | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours | Financement Prive et CR + Dotation conduite et kiosque
CRS | ATS | Brickaville | Andovoranto | Ambila Lemaitso | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | AΠR |  | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-02-13 | 2019-04-10 | 2019-08-10 | Exploitation | -
CRS | ATS | Brickaville | Fetraomby | Fetraomby | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | SEDERA |  |  |  |  | #N/A | OK | - | - | 70% | 2022-11-30 | 2022-12-23 | 2022-12-23 | En cours | Financement prive + Dotation conduite et kiosque
CRS | ATS | Brickaville | Mahatsara | Mahatsara | PPP | USAID | AEPP (BS, BP, PEC) | Bushproof | 2 ADH | 2019-05-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-05-09 | 2020-08-25 | 2021-08-13 | Exploitation | -
CRS | ATS | Brickaville | Ranomafana Est | Ranomafana Est | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | LOVA VELU | 2018-03-01 | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-16 | 2019-06-22 | 2020-08-10 | Exploitation | -
CRS | ATS | Brickaville | Razanaka | Razanaka | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Sandandrano | LOVA VELU | 2019-10-01 |  |  |  | #N/A | En cours | - | - | - | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours | Financement prive + Dotation conduite et kiosque
CRS | ATS | Toamasina II | Ambodiriana | Ambodiriana | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2019-06-01 | 2020-03-01 | #N/A |  | Clôturé | 2020-07-03 | - | 2020-07-23 | 100% | 2020-11-09 | 2020-12-09 | Done | Exploitation | -
CRS | ATS | Toamasina II | Ambodiriana | Analamangahazo | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2019-06-01 | 2020-03-01 | #N/A |  | Clôturé | 2020-07-03 | - | 2020-07-23 | 100% | 2020-11-10 | 2020-12-10 | Done | Exploitation | -
CRS | ATS | Toamasina II | Ambodiriana | Fontsimavo | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP | 2019-06-01 | 2020-03-01 | #N/A |  | Clôturé | 2020-07-03 | - | 2020-07-22 | 100% | 2020-11-10 | 2020-12-09 | Done | Exploitation | -
CRS | ATS | Toamasina II | Amboditandroroho | Amboakarivo | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | EATC |  | 2019-10-01 | #N/A |  | Clôturé | 2020-01-22 | - | 2020-01-21 | 100% | 2020-09-12 | 2020-09-16 | Done | Exploitation | -
CRS | ATS | Toamasina II | Amboditandroroho | Amboditandroroho | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | EATC |  | 2019-10-01 | #N/A |  | Clôturé | 2020-01-22 | - | 2020-01-20 | 100% | 2020-09-11 | 2020-09-15 | Done | Exploitation | -
CRS | ATS | Toamasina II | Amboditandroroho | Mahatsara | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | EATC |  | 2019-10-01 | #N/A |  | Clôturé | 2020-01-22 | - | 2020-01-21 | 100% | 2020-09-10 | 2020-09-16 | Done | Exploitation | -
CRS | ATS | Toamasina II | Ampasimadinika | Ampasimadinika | PPP | USAID | AEPP (BS, BP, PEC) | Sandandrano | 2 ADH | 2019-06-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-08-22 | 2020-08-24 | 2021-08-13 | Exploitation | -
CRS | ATS | Toamasina II | Ampasimbe Onibe | Ampasimbe Onibe | PPP | USAID | AEPG (BS, BP, PEC) | Bushproof | CREAT BTP | 2018-03-01 | 2018-04-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-04-30 | 2019-06-21 | 2020-08-29 | Exploitation | -
CRS | ATS | Toamasina II | Fanandrana | Fanandrana | PPP | charity: water | AEPP (BS, BP, PEC) | Zara-Rano | NMS | 2019-10-01 | 2020-02-01 | #N/A | 2020-02-01 | Clôturé | 2020-04-10 | 2020-03-19 | 2020-05-05 | 100% | 2020-11-05 | Done | Done | Exploitation | -
CRS | ATS | Toamasina II | Mahavelona Foulpointe | Bongabe | PPP+ | Privé | AEPG (BS, BP, PEC) | DREAH | Sandandrano | 2018-11-01 | 2021-11-15 | Validé |  | #N/A | En cours | - | - | - | 2022-12-15 | 2023-01-22 | 2023-01-22 | En cours | -
CRS | ATS | Toamasina II | Mahavelona Foulpointe | Mahavelona-Foulpointe | PPP | USAID | AEPP (BS, BP, PEC) | DREAH | Sandandrano |  | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-02-11 | 2019-04-09 | 2020-08-07 | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Ambalakondro | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2019-08-01 | #N/A |  | Clôturé | 2019-12-10 | 2019-12-10 | 2019-12-17 | 100% | 2020-03-18 | Done | Done | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Ambodirafia | PPP+ | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2020-02-01 | #N/A |  | Clôturé | 2020-05-05 | - | - | 100% | 2020-10-15 | Done | Done | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Maroangivy | PPP+ | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2020-02-01 | #N/A |  | Clôturé | 2020-05-05 | - | - | 100% | 2020-10-14 | Done | Done | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Sahambala | PPP | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2019-08-01 | #N/A |  | Clôturé | 2019-12-10 | 2019-12-10 | 2019-12-17 | 100% | 2020-03-17 | Done | Done | Exploitation | -
CRS | ATS | Toamasina II | Sahambala | Sahavongo | PPP+ | charity: water | AEPG (BS, BP, PEC) | Zara-Rano | CREAT BTP |  | 2020-02-01 | #N/A |  | Clôturé | 2020-05-05 | - | - | 100% | 2020-10-16 | Done | Done | Exploitation | -
CRS | ATS | Vatomandry | Ilaka Est | Ilaka-Est | PPP | USAID | AEPP (BS, BP, PEC) | Sandandrano | LOVA VELU |  | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-02-06 | 2019-04-11 | 2020-08-12 | Exploitation | -
CRS | ATS | Vatomandry | Niarovana Caroline | Niarovana Caroline | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | 2 ADH | 2018-03-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-01-22 | 2020-05-09 | 2021-08-14 | Exploitation | -
CRS | VKN | Antanifotsy | Ambatotsipihina | Ambatotsipihina | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | LOVA VELU | 2021-02-01 | 2021-08-04 | 2022-03-16 | 2022-01-10 | Clôturé | - | - | 2022-10-11 | 6.91% | 2023-01-09 | 2023-01-24 | 2023-07-25 12:00 | En cours | -
CRS | VKN | Antsirabe II | Ambohitsimanova | Ambohitsimanova | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | ACOGEMA | 2020-02-01 | 2020-06-30 | 2021-01-19 | 2020-09-15 | Clôturé | 2021-04-06 | 2021-05-07 | 2021-05-27 | 100% | 2021-08-23 | 2021-10-29 | 2022-06-23 | Exploitation | -
CRS | VKN | Antsirabe II | Antsoatany | Antsoatany | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | 2 ADH | 2020-02-01 | 2020-06-30 | 2021-01-06 | 2020-09-15 | Clôturé | 2021-04-06 | 2021-05-07 | 2021-05-30 | 100% | 2021-12-14 | 2022-01-14 | 2022-06-24 | Exploitation | -
CRS | VKN | Antsirabe II | Soanindrariny | Soanindrariny | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | EC ABRAHAM | 2020-02-01 | 2020-06-30 | 2021-01-11 | 2020-09-15 | Clôturé | 2021-04-06 | 2021-05-07 | 2021-06-01 | 100% | 2021-10-28 | 2021-11-23 | 2022-06-23 | Exploitation | -
CRS | VKN | Betafo | Alakamisy Anativato | Alakamisy Anativato | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano | [5 empty] | En cours | - | - | - | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours
CRS | VKN | Betafo | Ambohimanambola | Ambohimanambola | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | ACOGEMA | #N/A | 2021-07-17 | Validé | 2022-01-10 | Clôturé | - | - | 2022-09-23 | 69.54% | 2022-12-22 | 2023-01-06 | 2023-07-07 12:00 | En cours | -
CRS | VKN | Betafo | Mandritsara | Mandritsara | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano | [5 empty] | En cours | - | - | - | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours
CRS | VKN | Betafo | Soavina | Soavina | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano | [5 empty] | En cours | - | - | - | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours
WaterAid | ALMA | Amparafaravola | Amparafaravola | Ambongabe | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | EGC Tamby | 2018-11-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-09-11 | 2020-09-15 | 2022-12-22 | Attente RD | Systeme Ambongabe - Betatamo
WaterAid | ALMA | Amparafaravola | Amparafaravola | Betatamo | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | EGC Tamby | 2018-11-01 | 2019-06-01 | Validé |  | Clôturé | - | - | - | 100% | 2020-09-11 | 2020-09-15 | 2022-12-22 | Attente RD | Systeme Ambongabe - Betatamo
WaterAid | ALMA | Amparafaravola | Morarano Chrome | Morarano Chrome | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | LOVA VELU | 2019-09-01 | 2020-01-31 | 2020-11-18 |  | Clôturé | - | - | - | 100% | 2021-10-27 | 2022-10-04 | 2022-10-25 | Attente RD | Natao ny RT voalohany dia natao visite tech fa tsy nandeha ny rano, Nisy extension natao dia hiandrasana an'io ny RP
WaterAid | ALMA | Moramanga | Amboasary | Amboasary | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | DREAH | Naturano |  | En cours |  |  |  | En cours | - | - | - | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours | Natureau, LOVA VELU no nametraka offre, miandry valiny CAO
WaterAid | ALMA | Moramanga | Anosibe Ifody | Ambodinifody | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Rano an'ala B | 2018-11-01 | 2019-05-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-12-20 | 2020-09-09 | 2020-09-09 | Exploitation | -
WaterAid | ALMA | Moramanga | Anosibe Ifody | Tsarafasina | PPP+ | Privé | AEPG (BS, BP, PEC) | DREAH | Rano an'ala B | [5 empty] | - | - | 2022-04-14 | 85% | 2022-10-25 | 2022-11-25 | 2022-11-25 | En cours | Addendum signé en 2021
WaterAid | ALMA | Moramanga | Beforona | Ambinanisoavolo | PPP+ | Privé | AEPG (BS, BP, PEC) | DREAH | ACOGEMA | [5 empty] | - | - | 2022-04-05 | 90% | 2022-10-30 | 2022-11-30 | 2022-11-30 | En cours | -
WaterAid | ALMA | Moramanga | Beforona | Beforona | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | ACOGEMA | 2018-03-01 | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2019-01-24 | 2019-07-06 | 2020-09-08 | Exploitation | -
WaterAid | ALMA | Moramanga | Beforona | Marolafa | PPP+ | Privé | AEPG (BS, BP, PEC) | DREAH | ACOGEMA | [5 empty] | - | - | 2022-04-05 | 90% | 2022-10-30 | 2022-11-30 | 2022-11-30 | En cours | -
WaterAid | ALMA | Moramanga | Beforona | Marozevo/Soakambana | PPP+ | Privé | AEPG (BS, BP, PEC) | DREAH | ACOGEMA | [5 empty] | - | - | 2022-04-05 | 90% | 2022-10-30 | 2022-11-30 | 2022-11-30 | En cours | -
WaterAid | ALMA | Moramanga | Mandialaza | Mandialaza | Manifestation spontanée | Privé | AEPG (BS, BP, PEC) | Sandandrano | Rano an'ala B | 2019-09-01 | En cours |  |  |  | 11 Mars 2022 | - | Attente accord environnemental | - | 2022-12-15 | 2023-01-20 | 2023-01-20 | En cours | Financement: Commune, RANO An'ALA B, Fanamby, USAID
WaterAid | ALMA | Moramanga | Morarano Gara | Morarano Gara | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | Rano an'ala B | 2018-11-01 | 2020-11-11 | 2021-08-23 |  | Clôturé | - | - | 2022-05-25 | 90.32% | 2022-09-22 | 2022-11-22 | 2023-06-05 | RP et RD | -
WaterAid | ALMA | Moramanga | Sabotsy Anjiro | Sabotsy Anjiro | PPP | USAID | AEPG (BS, BP, PEC) | Sandandrano | RPIJ | 2018-11-01 | 2018-08-01 | Validé |  | Clôturé | - | - | - | 100% | 2018-12-18 | 2019-07-05 | 2020-09-08 | Exploitation | -
Formulas:
RD = [RP]+(390/2)
RT = [Démarrage travaux le]+90
RP = [RT]+15
Note on K16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par BP en Juillet 2018 APS fait par SDN en Novembre 2018
Note on L16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par BP en Juillet 2018
Note on K17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par BP en Juillet 2018 APS fait par SDN en Novembre 2018
Note on L17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par BP en Juillet 2018
Note on L29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Existence version Novembre 2019 et une nouvelle version en Septembre 2020 fait par BP
Note on G36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof
Note on G39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Sandandrano
Note on L46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APD fait par Sandandrano
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on G51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zara-Rano / Cost-share RANO WASH
Note on K53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: APS fait par Bushproof en Mars 2018

## INVEST-LOG GIC
GESTIONNAIRES INVESTISSEURS CONSTRUCTEURS 7 REGIONS D'INTERVENTION RANO WASH
NB | Les GICs | Logos | Investissements | Sites / Systemes d'AEP | Contribution du GIC | Contribution de la commune | Nombre de Systemes par GIC
14 | Mickael |  | 346020000 | - Ambalamahasoa / Dist. LALANGINA - Ambalatenina / Dist. IKONGO - Ambatofotsy / Dist. IKONGO - Ambodiara Sakorihy / Dist. IKONGO - Ambohitrova / Dist. VOHIPENO - Andrainjato / Dist. AMBALAVAO - Andranomiditra / Dist. VOHIBATO - Androy / Dist. LALANGINA - Antaretra / Dist. IFANADIANA - Ihazoara / Dist. VOHIBATO - Kianjanomby / Dist. IFANADIANA - Lokomby / Dist. VOHIPENO - Mahazoarivo / Dist. VOHIPENO - Manampatrana / Dist. IKONGO | 346020000 |  | 14
9 | CREAT BTP |  | 92490959 | - Ambalakondro / Dist. TOAMASINA II - Ambodirafia / Dist. TOAMASINA II - Ambodiriana / Dist. TOAMASINA II - Ampasimbe Onibe / Dist. TOAMASINA II - Analamangahazo / Dist. TOAMASINA II - Fontsimavo / Dist. TOAMASINA II - Maroangivy / Dist. TOAMASINA II - Sahambala / Dist. TOAMASINA II - Sahavongo / Dist. TOAMASINA II | 92490959 |  | 9
6 | ACOGEMA |  | 221307470 | - Ambinanisoavolo / Dist. MORAMANGA - Ambohimanambola / Dist. BETAFO - Ambohitsimanova / Dist. ANTSIRABE II - Beforona / Dist. MORAMANGA - Marolafa / Beforona / Dist. MORAMANGA - Marozevo / Soakambana / Dist. MORAMANGA - Ambatomarina / Dist. MANANDRIANA | 221307470 |  | 6
5 | 2ADH |  | 176722065 | - Ampasimadinika / Dist. TOAMASINA II - Antsoantany / Dist. ANTSIRABE II - Mahatsara / Dist. BRICKAVILLE - Niarovana Caroline / Dist. VATOMANDRY - Ampasimbe / Dist. BRICKAVILLE | 176722065 |  | 5
5 | LOVA VELU |  | 329163925.49 | - Ambatotsipihina / Dist. ANTANIFOTSY - Ilaka-Est / Dist. VATOMANDRY - Morarano Chrome / Dist. AMPARAFARAVOLA - Ranomafana -Est / Dist. BRICKAVILLE - Razanaka / Dist. BRICKAVILLE | 329163925.49 |  | 5
4 | Naturano |  | 126837500 | - Alakamisy Anativato / Dist. BETAFO - Amboasary Gara / Dist. MORAMANGA - Mandritsara / Dist. BETAFO - Soavina / Dist. BETAFO | 126837500 |  | 4
4 | Rano an'ala B |  | 136654531 | - Ambodinifody / Dist. MORAMANGA - Mandialaza / Dist. MORAMANGA - Morarano Gara / Dist. MORAMANGA - Tsarafasina / Dist. MORAMANGA | 136654531 |  | 4
3 | AΠR |  | 202934757 | - Ambila Lemaitso / Dist. BRICKAVILLE - Ilaka Centre / Dist. AMBOSITRA - Ivato Centre / Dist. AMBOSITRA | 202934757 |  | 3
3 | EATC |  | 132145055 | - Amboakarivo / Dist. TOAMASINA II - Amboditandroroho / Dist. TOAMASINA II - Mahatsara / Dist. TOAMASINA II | 132145055 |  | 3
3 | EC ABRAHAM |  | 211617980 | - Ampasimanjeva / Dist. MANAKARA ATSIMO - Soanindrariny / Dist. ANTSIRABE II - Vohitrindry / Dist. VOHIPENO | 211617980 |  | 3
3 | Fitahiana |  | 201055942 | - Fenomby / Dist. MANAKARA ATSIMO - Namorona / Dist. MANANJARY - Vohimasina Nord / Dist. MANAKARA ATSIMO | 201055942 |  | 3
2 | EGC Tamby |  | 200000000 | - Ambongabe / Dist. AMPARAFARAVOLA - Betatamo / Dist. AMPARAFARAVOLA | 200000000 |  | 2
2 | Miharintsoa |  | 35038417 | - Namoly / Dist. AMBALAVAO - Sendrisoa / Dist. AMBALAVAO | 35038417 |  | 2
2 | Sandandrano |  | 97981382 | - Mahavelona-Foulpointe / Dist. TOAMASINA II - Bongabe / Dist. TOAMASINA II | 97981382 |  | 2
1 | Bushproof |  | 0 | - Andemaka / Dist. VOHIPENO | 0 |  | 1
1 | Ecowin |  | 71688042 | - Andonabe / Dist. MANANJARY | 71688042 |  | 1
1 | LAZA |  | 598000 | - Andranovorivato / Dist. VOHIBATO | 598000 |  | 1
1 | NMS |  | 126520103 | - Fanandrana / Dist. TOAMASINA II | 126520103 |  | 1
1 | RPIJ |  | 66275746.68 | - Sabotsy Anjiro / Dist. MORAMANGA | 66275746.68 |  | 1
1 | SECOA |  | 40191350 | - Andrainjato -Est / Dist. LALANGINA | 40191350 |  | 1
1 | SEDERA |  | 61099788 | - Fetraomby / Dist. BRICKAVILLE | 61099788 | 8500000 | 1
| TOTAL CO-INVESTISSEMENT |  | 2876343013.17 |  |  |  | 72
Note on F4: Ambalamahasoa
Note on I4: Ambohitrova
Note on J4: Andrainjato
Note on K4: Andranomiditra
Note on L4: Androy
Note on M4: Antaretra
Note on N4: Ihazoara
Note on O4: Kianjanomby
Note on P4: Lokomby
Note on F6: AMBOHIMANAMBOLA 17%
Note on F8: AMBATOTSIPIHINA 16,14%

## ESE EN BESOIN DE CONTRAT
12 Contrat signe par MEAH (Par le ministre)
| ORGANISATONS | REGIONS | DISTRICTS | COMMUNE | SITES | GIC CONCERNES |  | 8 ENTREPRISES CONCERNES
1 | WaterAid | ALMA | Moramanga | Sabotsy Anjiro | SABOTSY ANJIRO | RPIJ | 1 system | 15 systemes
2 | WaterAid | ALMA | Moramanga | Beforona | BEFORONA | ACOGEMA | 1 system
3 | WaterAid | ALMA | Moramanga | Anosibe Ifody | ANOSIBE IFODY | RANO AN'ALA B | 1 system
4 | WaterAid | ALMA | Amparafaravola | Amparafaravola | AMPARAFARAVOLA | AGC TAMBY | 2 system
5 | CRS | ATS | Vatomandry | Ilaka Est | ILAKA EST | LOVA VELU SARL | 1 system
6 | CRS | ATS | Brickaville | Ranomafana Est | RANOMAFANA EST | LOVA VELU SARL | 1 system
7 | CRS | ATS | Toamasina II | Ampasimbe Onibe | AMPASIMBE ONIBE | CREAT BTP | 1 system
8 | CRS | ATS | Brickaville | Andovoranto | AMBILA LEMAITSO | ATTR | 1 system
9 | CARE | V7V | Ifanadiana | Antaretra | ANTARETRA | MICKAEL | 1 system
10 | CARE | V7V | Ikongo | Ambatofotsy | AMBATOFOTSY | MICKAEL | 3 system
11 | CARE | V7V | Ifanadiana | Kelilalina | KIANJANOMBY | MICKAEL | 1 system
12 | CARE | V7V | Ikongo | Manampatrana | MANAMPATRANA | MICKAEL | 1 system
19 contrats sont depose entre Q1-Q4 FY22 au niveau MEAH
| ORGANISATONS | REGIONS | DISTRICTS | COMMUNE | SITES | GIC CONCERNES
1 | CARE | V7V | Vohipeno | Lokomby | LOKOMBY | MICKAEL | 1 system | 12 ENTREPRISES CONCERNES
2 | CARE | V7V | Vohipeno | Andemaka | ANDEMAKA | BUSHPROOF | 1 system | 21 systemes
3 | CARE | V7V | Vohipeno | Vohitrindry | VOHITRINDRY | EC ABRAHAM | 1 system
4 | CARE | AMM | Manandriana | Ambatomarina | AMBATOMARINA | ACOGEMA | 1 system
5 | CARE | AMM | Ambositra | Ivato | IVATO CENTRE | ATTR | 1 system
6 | CARE | HTM | Lalangina | Androy | ANDROY | MICKAEL | 1 system
7 | CARE | HTM | Lalangina | Andrainjato Est | ANDRAINJATO EST | SECOA | 1 system
8 | CARE | V7V | Manakara Atsimo | Fenomby | FENOMBY | FITAHIANA | 1 system
9 | CARE | V7V | Mananjary | Andonabe | ANDONABE | ECOWIN | 1 system
10 | CRS | VKN | Antsirabe II | Antsoatany | ANTSOANTANY | 2ADH | 1 system
11 | CRS | VKN | Antsirabe II | Soanindrariny | SOANINDRARINY | EC ABRAHAM | 1 system
12 | CRS | VKN | Antsirabe II | Ambohitsimanova | AMBOHITSIMANOVA | ACOGEMA | 1 system
13 | CRS | ATS | Toamasina II | Mahavelona Foulpointe | MAHAVELONA-FOULPOINTE (Addendum) | SANDANDRANO | 1 system
14 | CRS | ATS | Vatomandry | Niarovana Caroline | NIAROVANA CAROLINE | 2ADH | 1 system
15 | CRS | ATS | Brickaville | Mahatsara | MAHATSARA | 2ADH | 1 system
16 | CRS | ATS | Toamasina II | Ampasimadinika | AMPASIMADINIKA | 2ADH | 1 system
17 | WaterAid | ALMA | Amparafaravola | Morarano Chrome | MORARANO CHROME | LOVA VELU SARL | 1 system
18 | WaterAid | ALMA | Moramanga | Anosibe Ifody | ANOSIBE IFODY (Addendum Tsarafasina) | RANO AN'ALA B | 1 system
19 | WaterAid | ALMA | Moramanga | Beforona | BEFORONA (Addendum: Marolafa/Ambinanay soavolo/Marozevo) | ACOGEMA | 3 systems
OBJECTIF Q1-Q3 FY23:
LES 37 CONTRATS ET ADDENDUMS AUX CONTRATS EN BESOIN DE SIGNATURE PAR LA COMMUNE ET MEAH
| ORGANISATONS | REGIONS | DISTRICTS | COMMUNE | SITES | GIC CONCERNES | CDG par organisation
1 | CARE | AMM | Ambositra | Ilaka Centre | Ilaka Centre | AΠR | 13 | 17 ENTREPRISES CONCERNES
1 | CARE | HTM | Ambalavao | Andrainjato | Andrainjato | Mickael |  | 37 systemes
1 | CARE | HTM | Ambalavao | Namoly | Namoly | Miharintsoa
1 | CARE | HTM | Ambalavao | Sendrisoa | Sendrisoa | Miharintsoa
1 | CARE | HTM | Lalangina | Ambalamahasoa | Ambalamahasoa | Mickael
1 | CARE | HTM | Vohibato | Andranomiditra | Andranomiditra | Mickael
1 | CARE | HTM | Vohibato | Andranovorivato | Andranovorivato | LAZA
1 | CARE | HTM | Vohibato | Ihazoara | Ihazoara | Mickael |  |  | 2022-04-21 | 309.632
1 | CARE | V7V | Mananjary | Namorona | Namorona | Fitahiana |  |  | 2023-02-24 15:10
1 | CARE | V7V | Vohipeno | Ambohitrova | Ambohitrova | Mickael
1 | CARE | V7V | Vohipeno | Mahazoarivo | Mahazoarivo | Mickael
1 | CARE | V7V | Manakara Atsimo | Ampasimanjeva | Ampasimanjeva | EC ABRAHAM
1 | CARE | V7V | Manakara Atsimo | Vohimasina Nord | Vohimasina Nord | Fitahiana
1 | CRS | ATS | Brickaville | Ampasimbe | Ampasimbe | 2ADH | 21
1 | CRS | ATS | Brickaville | Fetraomby | Fetraomby | SEDERA
1 | CRS | ATS | Brickaville | Razanaka | Razanaka | LOVA VELU
1 | CRS | ATS | Toamasina II | Ambodiriana | Ambodiriana | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Ambodiriana | Analamangahazo | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Ambodiriana | Fontsimavo | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Amboditandroroho | Amboakarivo | EATC |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Amboditandroroho | Amboditandroroho | EATC |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Amboditandroroho | Mahatsara | EATC |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Fanandrana | Fanandrana | NMS |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Mahavelona Foulpointe | Bongabe | Sandandrano
1 | CRS | ATS | Toamasina II | Sahambala | Ambalakondro | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Sahambala | Ambodirafia | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Sahambala | Maroangivy | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Sahambala | Sahambala | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | ATS | Toamasina II | Sahambala | Sahavongo | CREAT BTP |  | ZARA RANO | ok | 2022-12-14
1 | CRS | VKN | Antanifotsy | Ambatotsipihina | Ambatotsipihina | LOVAVELU SARL
1 | CRS | VKN | Betafo | Ambohimanambola | Ambohimanambola | ACOGEMA
1 | CRS | VKN | Betafo | Alakamisy Anativato | Alakamisy Anativato | Naturano
1 | CRS | VKN | Betafo | Mandritsara | Mandritsara | Naturano
1 | CRS | VKN | Betafo | Soavina | Soavina | Naturano
1 | WaterAid | ALMA | Moramanga | Amboasary | Amboasary | Naturano | 3
1 | WaterAid | ALMA | Moramanga | Mandialaza | Mandialaza | Rano an'ala B
1 | WaterAid | ALMA | Moramanga | Morarano Gara | Morarano Gara | Rano an'ala B
AU TOTAL : 68 CONTRATS DE DELEGATION DE GESTION POUR LES 73 SYSTEMES DE RANO WASH